## Sprint 1
High Level Sprint Planning
ID | Product Backlog | Priority | User Story | Story Point | Sprint | Current Team Velocity = 20 Story Points; 1 Story Point = 8 Hours of Coding
US-01 | Register as Staff | High | As a staff member, I want to register an account, so that I can access the application and view my schedules, room assignments, and cleaning tasks. Acceptance Criteria Given that I am a new staff member When I complete the registration form and submit my details Then my account should be created successfully and I should be able to access the application. Tasks Create Staff Registration Screen Create Personal Information Form Create Username and Password Fields Validate Mandatory Fields Verify Email Address Store User Information in Database Display Registration Success Message | 3 | 1 | Sprint Velocity | Developers | Output of Each week
[6 empty] | 120 | 30 | 15 | Consideration: We have 4 developer, and sprint is of 2 week
US-02 | Register as Supervisor | High | As a supervisor, I want to register an account, so that I can manage staff schedules and room assignments. Acceptance Criteria Given that I am a new supervisor When I complete the registration form and submit my details Then my account should be created successfully. Tasks Create Supervisor Registration Screen Create Supervisor Information Form Validate Registration Details Verify Email Address Create Supervisor Role Profile Store Registration Information Display Registration Confirmation | 3 | 1 | 120 | 30 | 15
US-03 | Login Functionality | High | As a user, I want to log into the application, so that I can access features based on my role. Acceptance Criteria Given that I have a registered account When I enter valid username and password Then I should be redirected to the appropriate dashboard. Tasks Create Login Screen Create Username Field Create Password Field Validate Credentials Authenticate User Redirect User Based on Role Display Login Error Messages | 3 | 1 | 120 | 30 | 15
US-04 | Forgot Password | Medium | As a user, I want to reset my password, so that I can regain access to my account. Acceptance Criteria Given that I have forgotten my password When I select the "Forgot Password" option and enter my registered email Then I should receive instructions to reset my password. Tasks Create Forgot Password Screen Create Email Verification Process Generate Password Reset Link Send Password Reset Email Create New Password Screen Validate New Password Display Password Reset Confirmation | 2 | 1 | 80 | 20 | 10
US-05 | Role-Based Access Control | High | As a user, I want access based on my role, so that I only see features relevant to my responsibilities. Acceptance Criteria Given that I am logged into the applicationWhen the system identifies my role Then I should only be able to access features assigned to my role. Tasks Define Staff Permissions Define Supervisor Permissions Define Admin Permissions Create Role Mapping Logic Restrict Unauthorized Access Create Role-Based Navigation Menu Test User Access Permissions | 5 | 1 | 200 | 50 | 25
| Complexity | Story Points
| Very Small | 1
| Small | 2
| Medium | 3
| Large | 5
| Complex | 8
| Very Complex | 13
Priority Index
High
Medium
Low

## Sprint 2
High Level Sprint Planning
ID | Product Backlog | Priority | User Story | Story Point | Sprint | Current Team Velocity = 20 Story Points; 1 Story Point = 8 Hours of Coding
US-06 | Staff Dashboard | High | As a supervisor, I want to view staff availability, so that I can create schedules and assign resources efficiently. Acceptance Criteria Given that staff members have submitted their availability When I access the availability screen Then I should be able to view all staff availability information. Tasks Create Availability Dashboard Display Staff Availability Search Staff Availability Filter Availability by Date Sort Availability Records Retrieve Availability Data from Database | 3 | 2 | Sprint Velocity | Developers | Output of Each week
[6 empty] | 120 | 30 | 15 | Consideration: We have 4 developer, and sprint is of 2 week
US-07 | Supervisor Dashboard | High | As a supervisor, I want to view a dashboard, so that I can monitor staff assignments, schedules, and cleaning progress. Acceptance Criteria Given that I am logged into the application When I access the Supervisor Dashboard Then I should be able to monitor staff schedules and room assignments. Tasks Create Supervisor Dashboard UI Display Staff Assignments Display Room Assignments Display Schedule Summary Display Cleaning Status Create Navigation Menu Fetch Operational Data | 5 | 2 | 200 | 50 | 25
US-08 | Input Available Hours | High | As a staff member, I want to enter my available working hours, so that supervisors can create schedules based on my availability. Acceptance Criteria Given that I am logged into the application When I enter my available working hours Then my availability should be saved successfully. Tasks Create Availability Form Create Date Selection Control Create Time Selection Control Validate Availability Entries Save Availability Data Display Success Message | 3 | 2 | 200 | 50 | 25
US-09 | View Staff Availability | High | As a supervisor, I want to view staff availability, so that I can create schedules and assign resources efficiently. Acceptance Criteria Given that staff members have submitted their availability When I access the availability screen Then I should be able to view all staff availability information. Tasks Create Availability Dashboard Display Staff Availability Search Staff Availability Filter Availability by Date Sort Availability Records Retrieve Availability Data from Database | 3 | 2 | 120 | 30 | 15

## Sprint 3
High Level Sprint Planning
ID | Product Backlog | Priority | User Story | Story Point | Sprint | Current Team Velocity = 20 Story Points; 1 Story Point = 8 Hours of Coding
US-10 | Display Available Rooms | High | As a supervisor, I want to view available rooms, so that I can assign staff to rooms requiring cleaning. Acceptance Criteria Given that rooms are available in the system When I access the room management screen Then I should be able to view all available rooms and their status. Tasks Create Room Management Screen Display Room List Display Room Status Filter Rooms by Status Search Rooms Retrieve Room Data from Database | 2 | 3 | Sprint Velocity | Developers | Output of Each week
[6 empty] | 80 | 20 | 10 | Consideration: We have 4 developer, and sprint is of 2 week
US-11 | Display Available Staff | High | As a supervisor, I want to view available staff members, so that I can allocate cleaning tasks efficiently. Acceptance Criteria Given that staff availability has been entered When I access the staff allocation screen Then I should be able to view available staff members. Tasks Create Staff Availability Screen Display Staff List Display Availability Status Search Staff Filter Available Staff Retrieve Staff Data from Database | 2 | 3 | 80 | 20 | 10
US-12 | Assign Staff to Room | High | As a supervisor, I want to assign staff members to rooms, so that cleaning activities can be completed efficiently. Acceptance Criteria Given that staff and rooms are available When I assign a staff member to a room Then the room assignment should be saved successfully. Tasks Create Assignment Screen Display Available Rooms Display Available Staff Create Assignment Logic Save Assignment Update Room Status Display Confirmation Message | 5 | 3 | 200 | 50 | 25
US-13 | Reassign Staff to Room | Medium | As a supervisor, I want to reassign staff members to different rooms, so that operational changes can be accommodated. Acceptance Criteria Given that a room assignment already exists When I update the assignment Then the new room assignment should be saved successfully. Tasks Display Existing Assignments Create Reassignment Functionality Update Room Assignment Save Changes Display Confirmation Message | 3 | 3 | 120 | 30 | 15
US-14 | Assignment Notifications | Low | As a staff member, I want to receive notifications when room assignments are updated, so that I am aware of my responsibilities. Acceptance Criteria Given that a room assignment has been created or updated When the assignment is saved Then the assigned staff member should receive a notification. Tasks Create Notification Service Generate Assignment Notification Send Notification to Staff Display Notification in Dashboard Store Notification History | 2 | 3 | 80 | 20 | 10